## Sheet1
No. | Task | Assignee | Expected Time [h] | Effective Time [h]
1.1 | Create Project Outline | Team | 10 | 11.5
1.2 | Identify Use Cases | Team | 8 | 6
2.3 | First Architecture determined | Team | 4 | 4
1.4 | Setup Development Environment | Team | 4 | 6 | 26 | 27.5
2.1 | Detailed Analysis and formulation of all Use Cases | Team | 16 | 16
2.2 | Define Domain Model | R. Emberger | 2 | 1.5
2.3 | Create Project Analysis Document | Team | 16 | 14 | 34 | 31.5
3.1 | Project Management | N. Eckhart | 4 | 1
3.2 | Finish Architecture Design based on previous sketches | S. Bösch | 6 | 4
3.3 | Create Class Diagram and define Class Responsibilities | R. Emberger | 8 | 10
3.4 | Create Interaction Diagrams | P. Meier | 6 | 8
3.5 | Create GUI Mockups and Description of the Game Interface | N. Eckhart | 8 | 4
3.6 | Update Glossary as needed | Team | 2 | 0.5 | 34 | 27.5
4.1 | Project Management | N. Eckhart | 4 | 3
4.2 | Compile all Artifacts from Iteration #3 into design document. | P. Meier | 6 | 8
4.3 | Add additional descriptions required for design document diagrams. | S. Bösch | 6 | 6
4.4 | Define UI Prototype parameters for implementation in the next iteration. | R. Emberger | 8 | 6.5
4.5 | Create game class with game loop. | N. Eckhart | 5 | 5
4.6 | Create map class that can load a simplified map from a file with only path and non-path tiles. (Only one layer.) | P. Meier, S. Bösch | 12 | 14
4.7 | Update Glossary as needed | Team | 2 | 0.5 | 43 | 43
5.1 | Project Management | N. Eckhart | 4 | 1.5
5.2 | Implement the layer class with three instances on the map. | S. Bösch | 12 | 11
5.3 | Create enemies that spawn on layers, move along the path, damage the player and carry a bounty. | N. Eckhart | 8 | 9.5
5.4 | Create the tower class with the firing, upgrading and destroy behavior classes. | R. Emberger | 14 | 12
5.5 | Create an asset manager class with a sprite sheet and connect with all entities. (Towers, Enemies, Tiles) | P. Meier | 8 | 8
5.6 | Create the in-game menu with all relevant information and buttons. (According to design mockups) | N. Eckhart | 12 | 15
5.7 | Implement win and lose conditions with the relevant game states (Menu State, Game Over State, Victory State) | P. Meier | 6 | 6
5.8 | Implement tower building via UI. | S. Bösch | 8 | 8
5.9 | Update Glossary as needed | Team | 2 | 1.5 | 74 | 72.5
6.1 | Project Management | N. Eckhart | 6 | 6
6.2 | Create user manual. | P. Meier | 18 | 15
6.3 | Improve enemy movement with a heat map per layer. | N. Eckhart | 10 | 11.5
6.4 | Implement multi layered towers. | S. Bösch | 16 | 14
6.5 | Enable towers to target and fire at enemies. | R. Emberger | 14 | 10
6.6 | Connect UI to tower destroy and upgrade functionality. | P. Meier | 8 | 8
6.7 | Write the final report document. | N. Eckhart, S. Bösch, R. Emberger | 24 | 18
6.8 | Update Glossary as needed | Team | 2 | 0.5 | 98 | 83
|  |  | 309 | 285